## Product backlog
PRODUCT BACKLOG
# | Item | Priority | Point | Status
1 | Draw Usecase Diagram | 3 | 30 | Done
2 | Draw ERD | 3 | 30 | Done
3 | Draw Physical Diagram | 3 | 30 | Done
4 | Draw Mockup UI | 1 | 10 | Done
6 | Implement UI to Prototype | 2 | 20 | Work in Progress
8 | Draw Class Diagram | 3 | 30
9 | Draw Sequence Diagram | 3 | 30
10 | Implement Base Component | - | - | -
| - Register | 4 | 40
| - Login | 2 | 20
| - Logout | 2 | 20
11 | Implement Tester features | - | - | -
| - Spelling test | 5 | 50
| - Grammar test | 5 | 50
| - Broken links test | 3 | 30
| - Broken pages test | 3 | 30
| - Missing files tetst | 3 | 30
| - Prohibited content test | 5 | 50
| - Mobile layout test | 3 | 30
| - Speed test | 3 | 30
| - JavaScript errors test | 3 | 30
| - Favicons test | 3 | 30
| - Cookie law test | 3 | 30
| - Server behavior test | 3 | 30
| - Pages test | 3 | 30
| - Contact details test | 3 | 30
| - Redirections test | 3 | 30
12 | Implement Admin features | - | - | -
| - Manage account | 2 | 20
| - Manage word repossitory | 3 | 30
| - Manage website's dictionary | 3 | 30
13 | Research + Training | - | - | -
| - Elastic Search | 3 | 30 | Work in Progress
| - Trie Tree Data Structure | 3 | 30 | Done
| - SpringBoot, JPA, Hibernate | 3 | 30 | Done
| - React JS | 3 | 30 | Work in Progress
14 | Document | - | -
| - SRS Document | 5 | 50
| - SDD Document | 5 | 50
| - WCS Summary | 5 | 50
| - WCS Paper | 5 | 50
| - Report 1 | 2 | 20 | Done
| - Report 2 | 2 | 20 | Wait for review
| - Report 3 | 2 | 20
| - Report 4 | 2 | 20
| - Report 5 | 2 | 20
| - Report 6 | 2 | 20
15 | System Test | 5 | 50

## Functions
Item # | Description | Priority | Point | Status